## Project Plan
PERSONAL DEVELOPMENT PLAN
| PROJECT TITLE |  | START DATE
| Hyper Island Final Project: SQL Murder Mystery |  | 2023-07-31 |  |  | PROJECT DURATION
| PROJECT OWNER |  |  |  |  | in days
| Eva Mayer |  | 2023-09-22 |  |  | 54
| WEEKS AND TASKS | STATUS | COMMENTS | START DATE | END DATE | DURATION in days
| WEEK 1: PROJECT INITIATION Understand project brief and course goals, project ideation | Complete |  | 2023-07-31 | 2023-08-06 | 7 | Not Started
R | – Project Kickoff | Complete | Crosscrew event | 2023-07-31 |  |  | In Progress
E | – Call with industry mentor | Complete | Discussion about project idea | 2023-08-02 |  |  | Complete
F | – Slack chat with industry mentor | Complete | Showing example project and asking further questions | 2023-08-03 |  |  | On Hold
L | WEEK 2: HOLIDAY | Complete |  | 2023-08-07 | 2023-08-13 | 7
E | – Call with internship mentor | Complete | Asked about project idea, discussed tools | 2023-08-07
C | WEEK 3: PROJECT PLANNING Create PDP, plan tasks and tools |  |  | 2023-08-14 | 2023-08-20 | 7
T | – Holiday final days | Complete | No progress | 2023-08-14 | 2023-08-17 | 4
| – PDP | Complete |  | 2023-08-18
& | – Detailed planning: tools and timeline | Complete |  | 2023-08-20
| – Research example project(s) | Complete |  | 2023-08-19 | 2023-08-21 | 3
D | WEEK 4: PROJECT LAUNCH AND EXECUTION Create story (GPT-4?), source data, data modeling |  |  | 2023-08-21 | 2023-08-27 | 7
O | – Mid-way presentation | Complete |  | 2023-08-22
C | WEEK 5: PROJECT EXECUTION Explore Power BI for data analysis and visualization | Complete |  | 2023-08-28 | 2023-09-03 | 7
U | – Do it in Tableau instead
M | WEEK 6: PROJECT EXECUTION Backend: suitable database, create and connect tables, SQL queries to solve mystery | Complete |  | 2023-09-04 | 2023-09-10 | 7
E | –
N | WEEK 7: PROJECT EXECUTION AND COMPLETION Frontend: make game accessible, testing | Complete |  | 2023-09-11 | 2023-09-17 | 7
T | –
| WEEK 8: SUBMISSION AND PRESENTATION Finalise and review project, prepare for presentation |  |  | 2023-09-18 | 2023-09-24 | 7
| – Assessment submission - check date! |  |  | 2023-09-19
| – Project presentation |  |  | 2023-09-21
| – Final project exhibition |  |  | 2023-09-22